## Dashboard
AI Device Inspector — Delivery Tracker
Live view of the developer backlog. Figures update automatically from the Task Tracker sheet.
By sprint
Total tasks | Sprint | Total | Done | % | Status | Count
Completed | Sprint 1 |  |  |  | Not Started
In progress | Sprint 2 |  |  |  | In Progress
In review | Sprint 3 |  |  |  | Blocked
Blocked | Sprint 4 |  |  |  | In Review
Not started | Test |  |  |  | Done
% complete (effort) | Go-live
% complete (count)
By workstream
| Workstream | Total | Done | %
WS1 · Foundations
WS2 · Capture
WS3 · AI engine
WS4 · Review & grading
WS5 · Records & data
WS6 · Insight & admin
General · Cross-cutting

## Lists (hidden)
Status | Priority | Sprint | Workstream
Not Started | High | Sprint 1 | WS1
In Progress | Medium | Sprint 2 | WS2
Blocked | Low | Sprint 3 | WS3
In Review |  | Sprint 4 | WS4
Done |  | Test | WS5
|  | Go-live | WS6
General

## Task Tracker
Task ID | Workstream | Deliverable | Task | Sprint | Priority | Assignee | Est (days) | Start | Due | Status | % Complete | Notes / blockers
T-001 | General | — | Repo scaffolding, monorepo & coding standards | Sprint 1 | High | e.g. Dev name | 1 | 2026-08-04 | 2026-08-05 | In Progress | 60%
T-002 | General | — | CI/CD pipeline (GitHub Actions) + SCA/SAST/secret scan | Sprint 1 | High |  | 2 |  |  | Not Started | 0%
T-003 | General | — | Terraform: staging & production environments | Sprint 1 | High |  | 2 |  |  | Not Started | 0%
T-004 | WS1 | D-05 | Design tokens + component library | Sprint 1 | High |  | 3 |  |  | Not Started | 0%
T-005 | WS1 | D-05 | App shell, navigation & layouts (3 surfaces) | Sprint 1 | High |  | 2 |  |  | Not Started | 0%
T-006 | WS1 | D-01 | Email/password auth + optional 2FA | Sprint 1 | High |  | 2 |  |  | Not Started | 0%
T-007 | WS1 | D-01 | Enterprise SSO (SAML/OIDC) + rotating JWT | Sprint 1 | High |  | 2 |  |  | Not Started | 0%
T-008 | WS1 | D-02 | Role model + permission matrix (server-side) | Sprint 1 | High |  | 2 |  |  | Not Started | 0%
T-009 | WS1 | D-02 | Per-role permission test suite | Sprint 1 | Medium |  | 1 |  |  | Not Started | 0%
T-010 | WS1 | D-03 | Postgres schema + migrations | Sprint 1 | High |  | 2 |  |  | Not Started | 0%
T-011 | WS1 | D-03 | Row-level security (multi-tenant isolation) | Sprint 1 | High |  | 2 |  |  | Not Started | 0%
T-012 | WS1 | D-04 | Station kiosk sessions (device tokens, idle lock, switch) | Sprint 1 | Medium |  | 2 |  |  | Not Started | 0%
T-013 | WS2 | D-06 | Six-state guided capture workflow UI | Sprint 2 | High |  | 3 |  |  | Not Started | 0%
T-014 | WS2 | D-07 | Barcode/QR scan + OCR service-tag reading | Sprint 2 | High |  | 2 |  |  | Not Started | 0%
T-015 | WS2 | D-07 | Device lookup (model / spec / history / warranty) | Sprint 2 | Medium |  | 1 |  |  | Not Started | 0%
T-016 | WS2 | D-08 | Camera controller integration (6-camera trigger) | Sprint 2 | High |  | 3 |  |  | Not Started | 0%
T-017 | WS2 | D-08 | Focus/exposure validation + per-angle retake | Sprint 2 | Medium |  | 2 |  |  | Not Started | 0%
T-018 | WS2 | D-08 | Presigned image uploads to object storage | Sprint 2 | High |  | 1 |  |  | Not Started | 0%
T-019 | WS2 | D-09 | Offline capture queue + reconnect sync | Sprint 2 | Medium |  | 2 |  |  | Not Started | 0%
T-020 | WS2 | — | Live station status over WebSocket | Sprint 2 | Medium |  | 1 |  |  | Not Started | 0%
T-021 | WS3 | D-10 | Defect taxonomy definition + sign-off | Sprint 2 | High |  | 1 |  |  | Not Started | 0%
T-022 | WS3 | — | Training-data labelling pipeline | Sprint 2 | High |  | 2 |  |  | Not Started | 0%
T-023 | WS3 | D-11 | Fine-tune detection model (v1) | Sprint 2 | High |  | 3 |  |  | Not Started | 0%
T-024 | WS3 | D-12 | Inference service (FastAPI + ONNX/TensorRT) | Sprint 2 | High |  | 3 |  |  | Not Started | 0%
T-025 | WS3 | D-12 | Confidence thresholds + auto-escalation | Sprint 2 | Medium |  | 1 |  |  | Not Started | 0%
T-026 | WS3 | D-11 | Detection storage (region / severity / heat map) | Sprint 2 | High |  | 2 |  |  | Not Started | 0%
T-027 | WS3 | — | Inference job queue (Redis + BullMQ) | Sprint 2 | High |  | 1 |  |  | Not Started | 0%
T-028 | WS3 | D-13 | Model versioning + result stamping | Sprint 2 | Medium |  | 1 |  |  | Not Started | 0%
T-029 | WS4 | D-14 | Annotated viewer (boxes, heat map, zoom-to-defect) | Sprint 3 | High |  | 3 |  |  | Not Started | 0%
T-030 | WS4 | D-14 | Cursor tool: resize / draw defect regions | Sprint 3 | High |  | 2 |  |  | Not Started | 0%
T-031 | WS4 | D-15 | Detection management (accept/reject/reclassify/merge) | Sprint 3 | High |  | 2 |  |  | Not Started | 0%
T-032 | WS4 | D-15 | Low-confidence queue + supervisor routing | Sprint 3 | Medium |  | 1 |  |  | Not Started | 0%
T-033 | WS4 | D-16 | Grading engine (cosmetic/functional + health score) | Sprint 3 | High |  | 3 |  |  | Not Started | 0%
T-034 | WS4 | D-16 | Per-client grade profiles (versioned) | Sprint 3 | High |  | 2 |  |  | Not Started | 0%
T-035 | WS4 | D-17 | Disposition rules + supervisor override w/ reason | Sprint 3 | Medium |  | 1 |  |  | Not Started | 0%
T-036 | WS3 | D-13 | Retrain loop: corrections into training set | Sprint 3 | Medium |  | 2 |  |  | Not Started | 0%
T-037 | General | — | Automated regression suite (build out) | Sprint 3 | High |  | 2 |  |  | Not Started | 0%
T-038 | WS5 | D-18 | Inspection history grid (virtualised, 16-col) | Sprint 4 | High |  | 3 |  |  | Not Started | 0%
T-039 | WS5 | D-18 | Search, filters, saved presets, bulk actions | Sprint 4 | High |  | 2 |  |  | Not Started | 0%
T-040 | WS5 | D-19 | Inspection record tabs + full-res viewer | Sprint 4 | High |  | 2 |  |  | Not Started | 0%
T-041 | WS5 | D-19 | Branded PDF certificate + tamper hash + share link | Sprint 4 | High |  | 2 |  |  | Not Started | 0%
T-042 | WS5 | D-20 | CSV import wizard (5-step) | Sprint 4 | Medium |  | 2 |  |  | Not Started | 0%
T-043 | WS5 | D-20 | Exports (CSV / XLSX / PDF / JSON) | Sprint 4 | Medium |  | 1 |  |  | Not Started | 0%
T-044 | WS5 | D-21 | REST API + OpenAPI + signed webhooks | Sprint 4 | High |  | 2 |  |  | Not Started | 0%
T-045 | WS5 | D-21 | ERP/WMS connector + ZPL label printing | Sprint 4 | Medium |  | 2 |  |  | Not Started | 0%
T-046 | WS6 | D-22 | Dashboard & live floor (tiles, KPIs, charts) | Sprint 4 | High |  | 3 |  |  | Not Started | 0%
T-047 | WS6 | D-23 | Analytics (throughput, grade dist, defect Pareto) | Sprint 4 | Medium |  | 2 |  |  | Not Started | 0%
T-048 | WS6 | D-24 | Administration (clients/users/stations/taxonomy/profiles) | Sprint 4 | High |  | 3 |  |  | Not Started | 0%
T-049 | WS6 | D-25 | Immutable audit log + export | Sprint 4 | High |  | 2 |  |  | Not Started | 0%
T-050 | WS6 | D-25 | Retention/purge + right-to-erasure + redaction | Sprint 4 | Medium |  | 2 |  |  | Not Started | 0%
T-051 | General | — | Accessibility pass (WCAG 2.2 AA) | Sprint 4 | Medium |  | 2 |  |  | Not Started | 0%
T-052 | General | — | Performance budget enforcement (LCP / INP / p95) | Sprint 4 | Medium |  | 1 |  |  | Not Started | 0%
T-053 | General | — | System integration testing (SIT) | Test | High |  | 3 |  |  | Not Started | 0%
T-054 | General | — | Regression suite green (3 consecutive runs) | Test | High |  | 2 |  |  | Not Started | 0%
T-055 | General | — | Data migration rehearsal + rollback drill | Test | Medium |  | 1 |  |  | Not Started | 0%
T-056 | WS3 | — | Model accuracy validation on holdout set | Test | High |  | 2 |  |  | Not Started | 0%
T-057 | General | — | UAT support (operator / supervisor scripts) | Test | High |  | 3 |  |  | Not Started | 0%
T-058 | General | — | Load & soak testing (3x peak, 24h) | Test | Medium |  | 2 |  |  | Not Started | 0%
T-059 | General | — | Third-party penetration test + remediation | Test | High |  | 3 |  |  | Not Started | 0%
T-060 | General | — | Failure drills (network / GPU / storage) | Test | Medium |  | 1 |  |  | Not Started | 0%
T-061 | General | — | Documentation (architecture, API, guides, runbooks) | Test | Medium |  | 3 |  |  | Not Started | 0%
T-062 | General | — | Training + recorded walkthroughs | Test | Medium |  | 1 |  |  | Not Started | 0%
T-063 | General | — | Pilot line monitoring + go-live cutover | Go-live | High |  | 3 |  |  | Not Started | 0%
HOW TO USE
• Fill the shaded input columns as work proceeds: Assignee, Start, Due, Status, % Complete, Notes.
• Status & Priority & Sprint & Workstream are dropdowns. Status colours the row; overdue Due dates turn red.
• The Dashboard sheet totals everything automatically — no need to edit it.
• Add a new task by copying a row; keep the Task ID unique (T-064, …).
Note on A2: Example row — overwrite Assignee / dates / Status / % as work begins.

## Milestones
ID | Milestone | Target | Type | Payment % | Status | Actual date | Notes
M1 | Foundations live | End W2 | Demo | 15% | Pending
M2 | First device graded end to end | End W4 | Demo | 15% | Pending
M3 | Review & grading accepted | End W6 | Demo | 15% | Pending
M4 | Feature complete · code freeze | End W8 | Gate | 20% | Pending
M5 | UAT & accuracy signed off | End W10 | Gate | 15% | Pending
M6 | Production go-live & handover | End W12 | Gate | 15% | Pending
— | Warranty end (final payment) | +90 days | — | 5% | Pending
Total